## Sheet1
Gap ID | Control ID | Gap | Expected State | Current State | Risk | Priority | Recommendation | Owner | Status
GAP-TPRM-001 | TPRM-C005 | Access review evidence incomplete | Periodic access reviews should be demonstrable. | Review process exists but evidence is incomplete. | Excessive access | High | Obtain current access review evidence and establish recurring review documentation. | Vendor Security | Open
GAP-TPRM-002 | TPRM-C009 | Penetration test evidence incomplete | Current penetration testing should be documented. | Testing occurs but recent evidence is incomplete. | Undetected vulnerabilities | High | Obtain current penetration-test summary and remediation status. | Vendor Security | Open
GAP-TPRM-003 | TPRM-C013 | DR testing evidence incomplete | Recovery testing should be periodically performed and documented. | Testing exists but evidence is incomplete. | Service disruption | Medium | Obtain latest DR test results and remediation actions. | Vendor Security | Open
GAP-TPRM-004 | TPRM-C015 | Data retention requirements unclear | Customer data retention should be clearly defined. | Retention requirements require clarification. | Data over-retention | High | Define contractual retention periods and deletion requirements. | Vendor Management / Privacy | Open
GAP-TPRM-005 | TPRM-C016 | Data deletion evidence incomplete | Secure customer data deletion should be demonstrable. | Process exists but evidence is incomplete. | Data exposure | High | Obtain deletion procedure and evidence of secure deletion capability. | Vendor Security / Privacy | Open
GAP-TPRM-006 | TPRM-C018 | Subprocessor assessment evidence incomplete | Critical subprocessors should undergo documented risk assessment. | Oversight exists but evidence is incomplete. | Fourth-party risk | High | Obtain subprocessor assessment evidence and establish annual review. | Vendor Management | Open
GAP-TPRM-007 | TPRM-C019 | Monitoring evidence incomplete | Security monitoring should be documented and demonstrable. | Monitoring exists but evidence is limited. | Delayed threat detection | High | Obtain monitoring documentation and appropriate evidence. | Vendor Security | Open
GAP-TPRM-008 | TPRM-C020 | Independent assurance evidence limited | Vendor should provide appropriate independent assurance. | Limited evidence provided. | Assurance risk | Medium | Request current independent assurance report or equivalent security evidence. | Vendor Management | Open